## Release Plan
Increment Plan
Incr. | Start | Days | End | Estimated Size | Real Size | Status | Release Date | Goal | % Esfuerzo vs Estimación
1 | 2021-09-06 | 5 | 2021-09-10 | 36.3 | 39 | Ongoing | 2021-09-03 | Entrega Sprint 0 (Conformacion de equipo / Idea / Roles / Documentacion Preliminar) | 107.4%
Unplanned
Unplanned
Unplanned
Unplanned
Unplanned
Sprint Plan
Sprint | Start | Days | End | Estimated Size | Real Size | Status | Release Date | Goal | Increment | % Error estimación
1 | 2021-09-06 | 1 | 2021-09-06 | 6.5 | 7 | Released | 2021-09-10 | Desarrollar Product Backlook Priorizado | 1 | 7.692%
1 | 2021-09-07 | 0.28571 | 2021-09-06 06:51 | 1.8 | 2 | Released | 2021-09-10 | Construir Repositorio (Github) donde integraran el Trabajo | 1 | 11.11%
1 | 2021-09-07 06:51 | 0.42857 | 2021-09-06 17:09 | 2.8 | 3 | Released | 2021-09-10 | Construir Archivo Gestion Configuracion | 1 | 7.143%
1 | 2021-09-07 17:09 | 0.42857 | 2021-09-07 03:26 | 2.7 | 3 | Ongoing | 2021-09-10 | Construir Historias de Usuario a desarrollar en Sprint No.1 | 1 | 11.11%
1 | 2021-09-08 03:26 | 1 | 2021-09-08 03:26 | 6.8 | 7 | Ongoing | 2021-09-10 | Creacion y configuracion cuenta Devops (SrumBoard y tareas) | 1 | 2.941%
1 | 2021-09-09 03:26 | 1 | 2021-09-09 03:26 | 6.6 | 7 | Planned | 2021-09-10 | Construccion Incial de MockUps | 1 | 6.061%
1 | 2021-09-10 03:26 | 0.71429 | 2021-09-09 20:34 | 4.6 | 5 | Planned | 2021-09-10 | Construccion Inicial de Diagrama UML | 1 | 8.696%
1 | 2021-09-10 20:34 | 0.71429 | 2021-09-10 13:43 | 4.5 | 5 | Planned | 2021-09-10 | Diligenciamiento de documento IEEE 29148 | 1 | 11.11%
Unplanned
Unplanned
Historias no asignadas |  |  |  | 0
Total Size |  |  |  | 36.3 | 39
|  |  |  | Estimadas | Reales
Formulas:
Start = IF(OR(B14="",[Incr.]=""),"",B14)
Start = IF(AND([Start, row above]<>"",[Days, row above]<>"",[Days]<>""),[Start, row above]+[Days, row above],"")
End = IF(OR([Start]="",[Days]=""),"",[Start]+[Days]-1)
End = IF(AND([Start]<>"",[Days]<>""),[Start]+[Days]-1,"")

## Product Backlog
Product Backlog
Story ID | Story name | Status | Size | Sprint | Priority | Story Type | Comments | Additional Comments
1 | Desarrollar Product Backlook Priorizado | Done | 1 | 0 | 1 | Documentacion | Se Desarrolla Product Backlog Priorizado | Se crea el Product baclook para identificar las tareas y tiempos aproximados en minutos
2 | Construir Repositorio (Github) donde integraran el Trabajo | Done | 1 | 1 | 1 | Documentacion | Se Construye Repositorio (Github) en Proyecto de Equipo, El Proyecto tiene tres fases (To Do, In Progress, Done)
3 | Construir Archivo Gestion Configuracion | Done | 2 | 1 | 1 | Documentacion | Stack: MEVN Front: Vue Back: JavaScript, Express, Node BD: Mongo
4 | Construir Historias de Usuario a desarrollar en Sprint No.1 | Done | 2 | 0 | 1 | Documentacion | Construccion Historias de Usuario Spring 1
5 | Construir Historias de Usuario a desarrollar en Sprint No.2 | Ongoing | 3 | 0 | 1 | Documentacion | Configuración inicial DevOps
6 | Instalación de todos los componentes para el desarrollo del proyecto | Done | 2 | 0 | 0 | Documentacion | Diseño mockups | Se realizo la instalación de todos los componentes recomendados
Proyecto
Académica
Académica
Note on C2: ====== ID#AAAAO20iw4E Use the following statuses (2021-09-03 00:19:36) Planned (or empty) Ongoing Done Removed The sheet uses the above statuses in the formatting and calculation formulas.
Note on D2: ====== ID#AAAAO20iw4I Petri Heiramo (2021-09-03 00:19:36) Story Points or Ideal Days
Note on E2: ====== ID#AAAAO20iw4A Petri Heiramo (2021-09-03 00:19:36) Create a release plan by assigning stories to planned sprints. If there are more stories in the backlog than in the plan, leave the remaining stories unassigned to sprints.
Note on F2: ====== ID#AAAAO20iw38 Petri Heiramo (2021-09-03 00:19:36) You may assign priorities to the stories, but keep in mind that priority does not always equal implementation order.